## Task List
NextPrep — Project Activity Chart
| Project Start Date: | 2026-07-15 |  | Project End Date: | 2026-09-25
Task ID | Module / Activity | Duration (Days) | Predecessor(s) | Start Date | End Date | Assigned To
P1 | Phase 0: Project Initiation & Planning | 10 | - | 2026-07-15 | 2026-07-24 | Lead
1 | Project Initiation & Planning | 2 | - | 2026-07-15 | 2026-07-16 | Vivek
2 | Literature Survey | 3 | 1 | 2026-07-18 | 2026-07-20 | Vivek
3 | Requirement Analysis | 3 | 2 | 2026-07-18 | 2026-07-20 | Vivek
4 | System Architecture | 3 | 3 | 2026-07-18 | 2026-07-20 | Vivek
5 | SRS Documentation | 4 | 4 | 2026-07-21 | 2026-07-24 | Vivek
P2 | Phase 1: Core System Development | 13 | - | 2026-07-25 | 2026-08-06 | Lead
6 | React Project Setup | 2 | 5 | 2026-07-25 | 2026-07-26 | Vaibhav
7 | Express Server Setup | 2 | 6 | 2026-07-25 | 2026-07-26 | Vivek
8 | PostgreSQL Installation & Database Design | 4 | 7 | 2026-07-25 | 2026-07-28 | Vansh
9 | User Authentication (Register/Login) | 4 | 8 | 2026-07-30 | 2026-08-02 | Vivek
10 | Frontend Authentication Pages | 3 | 9 | 2026-08-04 | 2026-08-06 | Vaibhav
P3 | Phase 2: AI Interview & Resume Modules | 19 | - | 2026-08-07 | 2026-08-25 | Lead
11 | Dashboard Development | 4 | 10 | 2026-08-07 | 2026-08-10 | Vaibhav
12 | Resume Analyzer Module | 4 | 11 | 2026-08-07 | 2026-08-10 | Vivek
13 | AI Interview Module (Local LLM Integration) | 5 | 12 | 2026-08-10 | 2026-08-14 | Vivek
14 | Question Generation System | 4 | 13 | 2026-08-16 | 2026-08-19 | Vivek
15 | Answer Evaluation System | 4 | 14 | 2026-08-16 | 2026-08-19 | Vivek
16 | Interview Session Management | 3 | 15 | 2026-08-23 | 2026-08-25 | Vivek
P4 | Phase 3: Platform Integration & Testing | 13 | - | 2026-08-26 | 2026-09-07 | Lead
17 | Interview History & Reports | 3 | 16 | 2026-08-26 | 2026-08-28 | Vivek
18 | Frontend-Backend API Integration | 4 | 17 | 2026-08-26 | 2026-08-29 | Vaibhav
19 | Database Integration & CRUD | 4 | 18 | 2026-08-26 | 2026-08-29 | Vansh
20 | User Profile & Settings | 3 | 19 | 2026-08-31 | 2026-09-02 | Vaibhav
21 | Admin Panel | 4 | 20 | 2026-08-31 | 2026-09-03 | Vivek
22 | Notifications & Email Integration | 3 | 21 | 2026-09-05 | 2026-09-07 | Vivek
P5 | Phase 4: Finalization & Deployment | 17 | - | 2026-09-09 | 2026-09-25 | Lead
23 | Unit Testing | 4 | 22 | 2026-09-09 | 2026-09-12 | Vivek
24 | Integration Testing | 4 | 23 | 2026-09-10 | 2026-09-13 | Vivek
25 | Security Testing | 4 | 24 | 2026-09-11 | 2026-09-14 | Vivek
26 | Performance Optimization | 3 | 25 | 2026-09-17 | 2026-09-19 | Vivek
27 | Bug Fixing & Stabilization | 4 | 26 | 2026-09-17 | 2026-09-20 | Vivek
28 | Final Review & Project Handover | 4 | 27 | 2026-09-22 | 2026-09-25 | Vivek

## Gantt Chart
NextPrep — Gantt Chart
Project Start: 15/07/26 ¦ Project End: 25/09/26
|  |  |  | 15 Jul 26 |  |  |  | 19 Jul 26 | [6 empty] | 26 Jul 26 | [6 empty] | 02 Aug 26 | [6 empty] | 09 Aug 26 | [6 empty] | 16 Aug 26 | [6 empty] | 23 Aug 26 | [6 empty] | 30 Aug 26 | [6 empty] | 06 Sep 26 | [6 empty] | 13 Sep 26 | [6 empty] | 20 Sep 26
ID | Module / Activity | Days | Assigned To | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
P1 | Phase 0: Project Initiation & Planning | 10 | Lead | bar: 15 Jul 26 W to 19 Jul 26 F
1 | Project Initiation & Planning | 2 | Vivek | 15 Jul 26 F: Vivek
2 | Literature Survey | 3 | Vivek | 19 Jul 26 T: Vivek
3 | Requirement Analysis | 3 | Vivek | 19 Jul 26 T: Vivek
4 | System Architecture | 3 | Vivek | 19 Jul 26 T: Vivek
5 | SRS Documentation | 4 | Vivek | 19 Jul 26 S: Vivek
P2 | Phase 1: Core System Development | 13 | Lead | bar: 19 Jul 26 S to 02 Aug 26 T
6 | React Project Setup | 2 | Vaibhav | 26 Jul 26 M: Vaibhav
7 | Express Server Setup | 2 | Vivek | 26 Jul 26 M: Vivek
8 | PostgreSQL Installation & Database Design | 4 | Vansh | 26 Jul 26 W: Vansh
9 | User Authentication (Register/Login) | 4 | Vivek | 02 Aug 26 M: Vivek
10 | Frontend Authentication Pages | 3 | Vaibhav | 02 Aug 26 F: Vaibhav
P3 | Phase 2: AI Interview & Resume Modules | 19 | Lead | bar: 02 Aug 26 F to 23 Aug 26 T
11 | Dashboard Development | 4 | Vaibhav | 09 Aug 26 T: Vaibhav
12 | Resume Analyzer Module | 4 | Vivek | 09 Aug 26 T: Vivek
13 | AI Interview Module (Local LLM Integration) | 5 | Vivek | 09 Aug 26 S: Vivek
14 | Question Generation System | 4 | Vivek | 16 Aug 26 T: Vivek
15 | Answer Evaluation System | 4 | Vivek | 16 Aug 26 T: Vivek
16 | Interview Session Management | 3 | Vivek | 23 Aug 26 W: Vivek
P4 | Phase 3: Platform Integration & Testing | 13 | Lead | bar: 23 Aug 26 W to 06 Sep 26 M
17 | Interview History & Reports | 3 | Vivek | 23 Aug 26 S: Vivek
18 | Frontend-Backend API Integration | 4 | Vaibhav | 30 Aug 26 S: Vaibhav
19 | Database Integration & CRUD | 4 | Vansh | 30 Aug 26 S: Vansh
20 | User Profile & Settings | 3 | Vaibhav | 30 Aug 26 T: Vaibhav
21 | Admin Panel | 4 | Vivek | 30 Aug 26 F: Vivek
22 | Notifications & Email Integration | 3 | Vivek | 06 Sep 26 T: Vivek
P5 | Phase 4: Finalization & Deployment | 17 | Lead | bar: 06 Sep 26 W to 20 Sep 26 F
23 | Unit Testing | 4 | Vivek | 13 Sep 26 S: Vivek
24 | Integration Testing | 4 | Vivek | 13 Sep 26 M: Vivek
25 | Security Testing | 4 | Vivek | 13 Sep 26 T: Vivek
26 | Performance Optimization | 3 | Vivek | 20 Sep 26 S: Vivek
27 | Bug Fixing & Stabilization | 4 | Vivek | 20 Sep 26 M: Vivek
28 | Final Review & Project Handover | 4 | Vivek | bar: 20 Sep 26 T to 20 Sep 26 F