## Task List
NextPrep — Project Activity Chart
| Project Start Date: | 2026-07-15 |  | Project End Date: | 2026-09-25
Task ID | Module / Activity | Duration (Days) | Predecessor(s) | Start Date | End Date | Assigned To
P1 | Phase 0: Project Initiation & Planning | 10 | - | 2026-07-15 | 2026-07-24 | Lead
1 | Project Initiation & Planning | 2 | - | 2026-07-15 | 2026-07-16 | Vivek
2 | Literature Survey | 3 | 1 | 2026-07-18 | 2026-07-20 | Vivek
3 | Requirement Analysis | 3 | 2 | 2026-07-18 | 2026-07-20 | Vivek
4 | System Architecture | 3 | 3 | 2026-07-18 | 2026-07-20 | Vivek
5 | SRS Documentation | 4 | 4 | 2026-07-21 | 2026-07-24 | Vivek
P2 | Phase 1: Core System Development | 13 | - | 2026-07-25 | 2026-08-06 | Lead
6 | React Project Setup | 2 | 5 | 2026-07-25 | 2026-07-26 | Vaibhav
7 | Express Server Setup | 2 | 6 | 2026-07-25 | 2026-07-26 | Vivek
8 | PostgreSQL Installation & Database Design | 4 | 7 | 2026-07-25 | 2026-07-28 | Vansh
9 | User Authentication (Register/Login) | 4 | 8 | 2026-07-30 | 2026-08-02 | Vivek
10 | Frontend Authentication Pages | 3 | 9 | 2026-08-04 | 2026-08-06 | Vaibhav
P3 | Phase 2: AI Interview & Resume Modules | 19 | - | 2026-08-07 | 2026-08-25 | Lead
11 | Dashboard Development | 4 | 10 | 2026-08-07 | 2026-08-10 | Vaibhav
12 | Resume Analyzer Module | 4 | 11 | 2026-08-07 | 2026-08-10 | Vivek
13 | AI Interview Module (Local LLM Integration) | 5 | 12 | 2026-08-10 | 2026-08-14 | Vivek
14 | Question Generation System | 4 | 13 | 2026-08-16 | 2026-08-19 | Vivek
15 | Answer Evaluation System | 4 | 14 | 2026-08-16 | 2026-08-19 | Vivek
16 | Interview Session Management | 3 | 15 | 2026-08-23 | 2026-08-25 | Vivek
P4 | Phase 3: Platform Integration & Testing | 13 | - | 2026-08-26 | 2026-09-07 | Lead
17 | Interview History & Reports | 3 | 16 | 2026-08-26 | 2026-08-28 | Vivek
18 | Frontend-Backend API Integration | 4 | 17 | 2026-08-26 | 2026-08-29 | Vaibhav
19 | Database Integration & CRUD | 4 | 18 | 2026-08-26 | 2026-08-29 | Vansh
20 | User Profile & Settings | 3 | 19 | 2026-08-31 | 2026-09-02 | Vaibhav
21 | Admin Panel | 4 | 20 | 2026-08-31 | 2026-09-03 | Vivek
22 | Notifications & Email Integration | 3 | 21 | 2026-09-05 | 2026-09-07 | Vivek
P5 | Phase 4: Finalization & Deployment | 17 | - | 2026-09-09 | 2026-09-25 | Lead
23 | Unit Testing | 4 | 22 | 2026-09-09 | 2026-09-12 | Vivek
24 | Integration Testing | 4 | 23 | 2026-09-10 | 2026-09-13 | Vivek
25 | Security Testing | 4 | 24 | 2026-09-11 | 2026-09-14 | Vivek
26 | Performance Optimization | 3 | 25 | 2026-09-17 | 2026-09-19 | Vivek
27 | Bug Fixing & Stabilization | 4 | 26 | 2026-09-17 | 2026-09-20 | Vivek
28 | Final Review & Project Handover | 4 | 27 | 2026-09-22 | 2026-09-25 | Vivek

## Gantt Chart
NextPrep — Activity / Gantt Chart
Project Start: 15-Jul-2026 ¦ Project End: 25-Sep-2026
|  |  |  | Jul 2026 | [16 empty] | Aug 2026 | [30 empty] | Sep 2026
ID | Module / Activity | Days | Assigned To | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
P1 | Phase 0: Project Initiation & Planning | 10 | Lead | bar: Jul 2026 15 to Jul 2026 24
1 | Project Initiation & Planning | 2 | Vivek | bar: Jul 2026 15 to Jul 2026 16
2 | Literature Survey | 3 | Vivek | bar: Jul 2026 18 to Jul 2026 20
3 | Requirement Analysis | 3 | Vivek | bar: Jul 2026 18 to Jul 2026 20
4 | System Architecture | 3 | Vivek | bar: Jul 2026 18 to Jul 2026 20
5 | SRS Documentation | 4 | Vivek | bar: Jul 2026 21 to Jul 2026 24
P2 | Phase 1: Core System Development | 13 | Lead | bar: Jul 2026 25 to Aug 2026 6
6 | React Project Setup | 2 | Vaibhav | bar: Jul 2026 25 to Jul 2026 26
7 | Express Server Setup | 2 | Vivek | bar: Jul 2026 25 to Jul 2026 26
8 | PostgreSQL Installation & Database Design | 4 | Vansh | bar: Jul 2026 25 to Jul 2026 28
9 | User Authentication (Register/Login) | 4 | Vivek | bar: Jul 2026 30 to Aug 2026 2
10 | Frontend Authentication Pages | 3 | Vaibhav | bar: Aug 2026 4 to Aug 2026 6
P3 | Phase 2: AI Interview & Resume Modules | 19 | Lead | bar: Aug 2026 7 to Aug 2026 25
11 | Dashboard Development | 4 | Vaibhav | bar: Aug 2026 7 to Aug 2026 10
12 | Resume Analyzer Module | 4 | Vivek | bar: Aug 2026 7 to Aug 2026 10
13 | AI Interview Module (Local LLM Integration) | 5 | Vivek | bar: Aug 2026 10 to Aug 2026 14
14 | Question Generation System | 4 | Vivek | bar: Aug 2026 16 to Aug 2026 19
15 | Answer Evaluation System | 4 | Vivek | bar: Aug 2026 16 to Aug 2026 19
16 | Interview Session Management | 3 | Vivek | bar: Aug 2026 23 to Aug 2026 25
P4 | Phase 3: Platform Integration & Testing | 13 | Lead | bar: Aug 2026 26 to Sep 2026 7
17 | Interview History & Reports | 3 | Vivek | bar: Aug 2026 26 to Aug 2026 28
18 | Frontend-Backend API Integration | 4 | Vaibhav | bar: Aug 2026 26 to Aug 2026 29
19 | Database Integration & CRUD | 4 | Vansh | bar: Aug 2026 26 to Aug 2026 29
20 | User Profile & Settings | 3 | Vaibhav | bar: Aug 2026 31 to Sep 2026 2
21 | Admin Panel | 4 | Vivek | bar: Aug 2026 31 to Sep 2026 3
22 | Notifications & Email Integration | 3 | Vivek | bar: Sep 2026 5 to Sep 2026 7
P5 | Phase 4: Finalization & Deployment | 17 | Lead | bar: Sep 2026 9 to Sep 2026 25
23 | Unit Testing | 4 | Vivek | bar: Sep 2026 9 to Sep 2026 12
24 | Integration Testing | 4 | Vivek | bar: Sep 2026 10 to Sep 2026 13
25 | Security Testing | 4 | Vivek | bar: Sep 2026 11 to Sep 2026 14
26 | Performance Optimization | 3 | Vivek | bar: Sep 2026 17 to Sep 2026 19
27 | Bug Fixing & Stabilization | 4 | Vivek | bar: Sep 2026 17 to Sep 2026 20
28 | Final Review & Project Handover | 4 | Vivek | bar: Sep 2026 22 to Sep 2026 25